## main_data
Project Name | Contractor Name | Contractor Category | Task | Month | Planned Cost | Actual Cost | Variance
The Ark: Origin | StrongBuild RCC Contractors | RCC / Structural Work | Slab Cleaning | 2023-10-01 | 520000 | 545000 | 25000
The Ark: Origin | StrongBuild RCC Contractors | RCC / Structural Work | Slab Cleaning | 2023-11-01 | 500000 | 510000 | 10000
The Ark: Origin | StrongBuild RCC Contractors | RCC / Structural Work | Slab Cleaning | 2023-12-01 | 450000 | 495000 | 45000
The Ark: Origin | Shree Brickwork Solutions | Masonry / Brickwork | Brick Work | 2024-01-01 | 400000 | 380000 | -20000
The Ark: Origin | Shree Brickwork Solutions | Masonry / Brickwork | Brick Work | 2024-02-01 | 420000 | 410000 | -10000
The Ark: Origin | Shree Brickwork Solutions | Masonry / Brickwork | Brick Work | 2024-03-01 | 450000 | 440000 | -10000
The Ark: Origin | Perfect Plaster Works | Plaster | Cement Plaster | 2024-04-01 | 380000 | 400000 | 20000
The Ark: Origin | Perfect Plaster Works | Plaster | Cement Plaster | 2024-05-01 | 390000 | 415000 | 25000
The Ark: Origin | Interior POP Experts | POP / Gypsum | POP Plaster | 2024-06-01 | 350000 | 360000 | 10000
The Ark: Origin | Interior POP Experts | POP / Gypsum | POP Plaster | 2024-07-01 | 360000 | 390000 | 30000
The Ark: Origin | Sai Electricals | Electrical Work | Electrical Conduits | 2024-06-01 | 300000 | 290000 | -10000
The Ark: Origin | Sai Electricals | Electrical Work | Electrical Conduits | 2024-07-01 | 320000 | 310000 | -10000
The Ark: Origin | Omkar Plumbing Services | Plumbing Work | Plumbing | 2024-07-01 | 280000 | 295000 | 15000
The Ark: Origin | Omkar Plumbing Services | Plumbing Work | Plumbing | 2024-08-01 | 300000 | 330000 | 30000
The Ark: Origin | AquaSeal Waterproofing | Waterproofing | Waterproofing | 2024-08-01 | 260000 | 280000 | 20000
The Ark: Origin | AquaSeal Waterproofing | Waterproofing | Waterproofing | 2024-09-01 | 270000 | 300000 | 30000
The Ark: Origin | TileCraft Services | Tiling | Tiling - Floors | 2024-09-01 | 310000 | 280000 | -30000
The Ark: Origin | Marble & Granite Hub | Granite / Marble | Tiling - Granite | 2024-10-01 | 450000 | 450000 | 0
The Ark: Origin | Prime Door & Window Systems | Doors & Windows | (D&W) - Door Frames | 2024-10-01 | 380000 | 390000 | 10000
The Ark: Origin | Prime Door & Window Systems | Doors & Windows | (D&W) - Door Shutter + Hardware | 2024-11-01 | 420000 | 460000 | 40000
The Ark: Origin | ColorWorks Painting Co. | Painting & Touchup | Painting & Touchup | 2024-11-01 | 300000 | 340000 | 40000
The Ark: Origin | ColorWorks Painting Co. | Painting & Touchup | Cleaning | 2024-12-01 | 200000 | 210000 | 10000

## Sheet1
Data returned for Sum of Variance, (D&W) - Door Frames, All - All (First 1000 rows).
Cost_Data[Project Name] | Cost_Data[Contractor Name] | Cost_Data[Contractor Category] | Cost_Data[Task] | Cost_Data[Month] | Cost_Data[Planned Cost] | Cost_Data[Actual Cost] | Cost_Data[Variance]
The Ark: Origin | Prime Door & Window Systems | Doors & Windows | (D&W) - Door Frames | 2024-10-01 | 380000 | 390000 | 10000

## Cost_Analysis
Row Labels | Sum of Actual Cost | Sum of Planned Cost | Sum of Variance | Row Labels | Sum of Variance
(D&W) - Door Frames | 390000 | 380000 | 10000 | (D&W) - Door Frames | 10000
(D&W) - Door Shutter + Hardware | 460000 | 420000 | 40000 | (D&W) - Door Shutter + Hardware | 40000
Brick Work | 1230000 | 1270000 | -40000 | Brick Work | -40000
Cement Plaster | 815000 | 770000 | 45000 | Cement Plaster | 45000
Cleaning | 210000 | 200000 | 10000 | Cleaning | 10000
Electrical Conduits | 600000 | 620000 | -20000 | Electrical Conduits | -20000
Painting & Touchup | 340000 | 300000 | 40000 | Painting & Touchup | 40000
Plumbing | 625000 | 580000 | 45000 | Plumbing | 45000
POP Plaster | 750000 | 710000 | 40000 | POP Plaster | 40000
Slab Cleaning | 1550000 | 1470000 | 80000 | Slab Cleaning | 80000
Tiling - Floors | 280000 | 310000 | -30000 | Tiling - Floors | -30000
Tiling - Granite | 450000 | 450000 | 0 | Tiling - Granite | 0
Waterproofing | 580000 | 530000 | 50000 | Waterproofing | 50000
Grand Total | 8280000 | 8010000 | 270000 | Grand Total | 270000
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Cost Control & Variance Analysis
Analysing project planned cost and budget overruns
Key Insights: • Brickwork & Slab Cleaning show highest overruns • Electrical works are within budget • Waterproofing costs trend above plan in later months • Cost overruns increase towards project completion